JOBALIGN
Agile Sprint Planning – 2 Week MVP

AI-Powered Job & Skill Alignment System

# 1. Project Overview

JobAlign is an AI-powered job and skill alignment system supporting Candidate, Recruiter and Administrator roles. The 2-week sprint focuses on a Minimum Viable Product (MVP) containing only the Must-Have functionality required to demonstrate the core job-to-skill matching workflow.

| Item | Details |
| --- | --- |
| Project | JobAlign – AI-powered job and skill alignment system |
| Methodology | Scrum-based Agile planning |
| Sprint Duration | 2 Weeks / 10 Working Days |
| Sprint Type | MVP Delivery |
| Primary Roles | Candidate, Recruiter, Administrator |
| Technology Context | Microsoft SQL Server, Entity Framework Core, External AI Service |

# 2. Sprint Goal

Deliver a working end-to-end demonstration where a Recruiter can post a job, the system extracts and normalizes job details and skills using AI, a Candidate can analyze the job against their skill profile, and JobAlign displays a match score, matched/missing skills, and AI-generated skill-gap feedback.

# 3. Sprint Backlog

| ID | User Story | Story Points | Priority |
| --- | --- | --- | --- |
| US-01 | User Authentication and Basic Roles | 3 | Must Have |
| US-02 | Candidate Basic Profile and Skills | 5 | Must Have |
| US-03 | Canonical Skills and Aliases | 5 | Must Have |
| US-04 | Recruiter Posts a Job | 3 | Must Have |
| US-05 | AI Extracts Job Details and Skills | 8 | Must Have |
| US-06 | Job-Fit Analysis with Stored Snapshot | 8 | Must Have |
| US-07 | Display Matched and Missing Skills | 5 | Must Have |
| US-08 | AI Generates Skill-Gap Feedback | 5 | Must Have |
|  | Total | 42 |  |

# 4. Two-Week Sprint Schedule

## Week 1 – Foundation & Core Data

| Day | Focus | Stories | Deliverable |
| --- | --- | --- | --- |
| Day 1 – Monday | Identity & Authentication | US-01 | Registration, login and user roles |
| Day 2 – Tuesday | Roles & Skill Foundation | US-01, US-03 | Role authorization, Skills and SkillAliases |
| Day 3 – Wednesday | Candidate Profile | US-02 | Candidate can create profile and add skills |
| Day 4 – Thursday | Skill Normalization | US-02, US-03 | Proficiency, duplicate prevention and alias mapping |
| Day 5 – Friday | Job Posting Foundation | US-04 | Recruiter can create and save a job posting |

Week 1 Milestone: Working identity, candidate/recruiter foundation, normalized skill model, and basic job-posting workflow.

## Week 2 – AI Integration & Matching

| Day | Focus | Stories | Deliverable |
| --- | --- | --- | --- |
| Day 6 – Monday | AI Integration | US-05 | External AI service connected |
| Day 7 – Tuesday | AI Extraction | US-05 | Title, required/preferred skills and confidence extracted |
| Day 8 – Wednesday | Job Analysis | US-06 | Job-fit analysis and stored match score |
| Day 9 – Thursday | Skill Display | US-07 | Matched and missing skills displayed |
| Day 10 – Friday | AI Feedback & Demo | US-08 | Personalized feedback, testing and demo-ready MVP |

# 5. Technical Work Breakdown

| Area | Planned Work |
| --- | --- |
| Backend | ASP.NET Core Web API, authentication, authorization, candidate/recruiter APIs, job APIs and analysis APIs |
| Database | SQL Server with Entity Framework Core; Users, Roles, Candidates, Recruiters, Organizations, Skills, JobPostings, JobExtractions, JobAnalyses and feedback tables |
| Frontend | Simple MVC or React minimal UI for the core MVP workflow |
| AI | External AI service for job extraction and personalized skill-gap feedback |
| Testing | Unit, integration, negative and end-to-end testing for critical paths |

# 6. Scrum Ceremonies

| Ceremony | When | Duration | Purpose |
| --- | --- | --- | --- |
| Sprint Planning | Monday, Week 1 | 2 hours | Select stories, define sprint goal and confirm dependencies |
| Daily Scrum | Every working day | 15 minutes | Inspect progress, blockers and coordination |
| Mid-Sprint Review | Friday, Week 1 | 1 hour | Review progress and adjust within sprint scope |
| Backlog Refinement | Mid-sprint | 30–45 minutes | Clarify and estimate upcoming work |
| Sprint Review & Demo | Friday, Week 2 | 1 hour | Demonstrate the completed MVP |
| Retrospective | Friday, Week 2 | 45 minutes | Identify improvements for the next sprint |

# 7. Definition of Done

Feature is implemented and code-reviewed.

Unit tests pass.

Integration tests pass for the end-to-end workflow.

Database constraints match the design.

Authentication and authorization are enforced.

AI failure does not block job saving.

Job analysis completes within 10 seconds.

The completed increment is demo-ready.

# 8. Sprint Success Criteria

| Metric | Target |
| --- | --- |
| End-to-End Demo | Recruiter posts job → AI extracts → Candidate analyzes → Feedback shown |
| Test Coverage | Critical paths covered |
| Performance | Job analysis completes in less than 10 seconds |
| Code Quality | No critical blockers |

# 9. Out of Scope for This Sprint

The following features are deferred to future sprints to maintain the 2-week MVP scope:

Resume upload

Job comparison

Saved jobs

Job summary

Admin moderation

Reports and statistics

Education, experience, projects and certifications

Job completeness review

# 10. Final MVP Workflow

Recruiter Login → Create Job Posting → AI Extraction → Skill Normalization → Candidate Login → Candidate Skill Profile → Job Analysis → Match Score → Matched/Missing Skills → AI Skill-Gap Feedback

# 11. Sprint Risks & Mitigation

| Risk | Impact | Mitigation |
| --- | --- | --- |
| AI service downtime | High | Keep AI extraction separate and support Failed status/retry. |
| Low AI confidence | Medium | Store confidence score for future review. |
| Skill synonym inconsistency | High | Use canonical Skills and SkillAliases with normalization tests. |
| Time constraint | High | Implement only Must-Have MVP stories. |
| Slow analysis | High | Store analysis results and test performance against the 10-second target. |

# 12. Conclusion

This 2-week Agile sprint delivers a focused JobAlign MVP demonstrating the project's core value: AI-powered job extraction, skill normalization and matching, job-fit scoring, and personalized skill-gap feedback. Non-essential features remain deferred so the team can complete a working and demonstrable increment within the constrained timeline.